## KYO-JC-KC1
KYO-JC-KC1 Schedule
Stage | List | Start | Days | End | Duty | Remark
Tooling | Tooling Confirm | 2026-04-22 | 1 | 2026-04-22 | Customer
RX module | RX Module | 2026-04-27 | 26 | 2026-05-22 | SPS
| RX Module Assembly | 2026-05-23 | 4 | 2026-05-26 | SPS
| RX Module Testing | 2026-05-26 | 3 | 2026-05-28 | SPS
| RX Module Delivery | 2026-05-29 | 4 | 2026-06-01 | SPS | ETA MCO office (22set)
DMT0 | T0 (without texture) | 2026-04-22 | 43 | 2026-06-03 | ISSUI
| T0 Assmebly | 2026-06-05 | 8 | 2026-06-12 | SPS
| T0 Testing | 2026-06-12 | 5 | 2026-06-16 | SPS
| T0 Delivery | 2026-06-16 | 4 | 2026-06-19 | SPS | ETA MCO office (32set)
DMT1 | T1 (T-final sample) | 2026-06-12 | 15 | 2026-06-26 | ISSUI
| T1 Assembly | 2026-06-30 | 8 | 2026-07-07 | MNS
| T1 Testing | 2026-07-07 | 4 | 2026-07-10 | MNS
| T1 Delivery | 2026-07-10 | 4 | 2026-07-13 | MNS | ETA MCO office (32set)
Confirm | DMT0 Verification | 2026-06-22 | 14 | 2026-07-05 | Customer
| DMT0 Confirm | 2026-07-05 | 2 | 2026-07-06 | Customer
| DMT1 Verification | 2026-07-15 | 14 | 2026-07-28 | Customer
| DMT1 Confirm | 2026-07-28 | 2 | 2026-07-29 | Customer
| Offical PO for MP | 2026-07-29 | 1 | 2026-07-29 | Customer | Qty : TBD
MP | Case Injection | 2026-07-30 | 35 | 2026-09-02 | ISSUI
| Material Ready | 2026-07-30 | 40 | 2026-09-07 | MNS
| Mass Production | 2026-09-07 | 14 | 2026-09-20 | MNS
| Delivery | 2026-09-20 | 14 | 2026-10-03 | MNS | by ocean
Note. The RX connector for MP will use Korean company. The delivery date of Chinese company has been changed to 12~16 weeks.
Revision history
2026-05-11 | Switch KC1 and KC2 schedule
2026-05-28 | Changed DMT1 verification time to 14 days.
Formulas:
End = [Start]+[Days]-1
Start = [End, row above]+1
Start = [End, row above]

## KYO-JC-KC2
KYO-JC-KC2 Schedule
Stage | List | Start | Days | End | Duty | Remark
Tooling | Tooling Confirm | 2026-04-22 | 1 | 2026-04-22 | Customer
DMT0 | T0 (without texture) | 2026-04-22 | 43 | 2026-06-03 | ISSUI
| T0 Assmebly | 2026-06-05 | 5 | 2026-06-09 | SPS
| T0 Testing | 2026-06-09 | 4 | 2026-06-12 | SPS
| T0 Delivery | 2026-06-12 | 4 | 2026-06-15 | SPS | ETA MCO office (32set)
DMT1 | T1 (T-final sample) | 2026-06-09 | 8 | 2026-06-16 | ISSUI
| T1 Assembly | 2026-06-18 | 5 | 2026-06-22 | MNS
| T1 Testing | 2026-06-22 | 4 | 2026-06-25 | MNS
| T1 Delivery | 2026-06-25 | 5 | 2026-06-29 | MNS | ETA MCO office (102set)
Confirm | DMT0 Verification | 2026-06-17 | 14 | 2026-06-30 | Customer
| DMT0 Confirm | 2026-06-30 | 2 | 2026-07-01 | Customer
| DMT1 Verification | 2026-07-01 | 14 | 2026-07-14 | Customer
| DMT1 Confirm | 2026-07-14 | 3 | 2026-07-16 | Customer
| Offical PO for MP | 2026-07-16 | 1 | 2026-07-16 | Customer | Qty : TBD
MP | Case Injection | 2026-07-17 | 35 | 2026-08-20 | ISSUI
| Material Ready | 2026-07-17 | 40 | 2026-08-25 | MNS
| Mass Production | 2026-08-25 | 14 | 2026-09-07 | MNS
| Delivery | 2026-09-07 | 14 | 2026-09-20 | MNS | by ocean
Note. The RX connector for MP will use Korean company. The delivery date of Chinese company has been changed to 12~16 weeks.
Revision history
2026-05-11 | Switch KC1 and KC2 schedule
2026-05-19 | Changed 70set balance Qty assembly schedule.
2026-05-28 | Changed DMT1 verification time to 14 days.
Formulas:
End = [Start]+[Days]-1
Start = [End, row above]
Start = [End, row above]+2

## KYO-JC-DG1
KYO-JC-DG1 Schedule
Stage | List | Start | Days | End | Duty | Remark
Tooling | Tooling Confirm | 2026-04-24 | 1 | 2026-04-24 | Customer
DMT0 | T0 (without texture) | 2026-04-24 | 36 | 2026-05-29 | WJM
| T0 Assmebly | 2026-06-01 | 10 | 2026-06-10 | MNS/SPS
| T0 Testing | 2026-06-10 | 3 | 2026-06-12 | SPS
| T0 Delivery | 2026-06-12 | 4 | 2026-06-15 | SPS | ETA MCO office (32set)
DMT1 | T1 (T-final sample) | 2026-06-10 | 8 | 2026-06-17 | WJM
| T1 Assembly | 2026-06-19 | 7 | 2026-06-25 | MNS
| T1 Testing | 2026-06-25 | 5 | 2026-06-29 | MNS
| T1 Delivery | 2026-06-29 | 3 | 2026-07-01 | MNS | ETA MCO office (32set)
Confirm | DMT0 Verification | 2026-06-17 | 14 | 2026-06-30 | Customer
| DMT0 Confirm | 2026-06-30 | 2 | 2026-07-01 | Customer
| DMT1 Verification | 2026-07-03 | 14 | 2026-07-16 | Customer
| DMT1 Confirm | 2026-07-16 | 2 | 2026-07-17 | Customer
| Offical PO for MP | 2026-07-17 | 1 | 2026-07-17 | Customer | Qty : TBD
MP | Case Injection | 2026-07-20 | 30 | 2026-08-18 | WJM
| Material Ready | 2026-07-18 | 40 | 2026-08-26 | MNS
| Mass Production | 2026-08-26 | 13 | 2026-09-07 | MNS
| Delivery | 2026-09-07 | 14 | 2026-09-20 | MNS | by ocean
Note. The RX connector for MP will use Korean company. The delivery date of Chinese company has been changed to 12~16 weeks.
Revision history
2026-05-28 | Changed DMT1 verification time to 14 days.
Formulas:
End = [Start]+[Days]-1
Start = [End, row above]
Start = [End, row above]+3

## TOTAL (hidden)
ZEN-TX-STD6 Project Schedule | [5 empty] | ZEN-TX-STD5 Project Schedule | [5 empty] | ZEN-RX-PC5 Project Schedule
Stage | List | Start | Days | End | Remark | Stage | List | Start | Days | End | Remark | Stage | List | Start | Days | End | Remark
Start | Project Start | 2020-10-08 | 108 | 2021-01-23 |  | Start | Project Start | 2020-10-12 | 108 | 2021-01-27 |  | Start | Project Start | 2020-10-12 | 111 | 2021-01-30
Tooling | 3D verification | 2020-10-09 | 3 | 2020-10-11 |  | Tooling | 3D verification | 2020-10-13 | 2 | 2020-10-14 |  | Tooling | 3D verification | 2020-10-13 | 2 | 2020-10-14
| Tooling start | 2020-10-12 | 30 | 2020-11-10 | depends on vender |  | Tooling start | 2020-10-15 | 30 | 2020-11-13 | depends on vender |  | Tooling start | 2020-10-15 | 30 | 2020-11-13 | depends on vender
| T0 | 2020-11-10 | 3 | 2020-11-12 |  |  | T0 | 2020-11-13 | 3 | 2020-11-15 |  |  | T0 | 2020-11-13 | 3 | 2020-11-15
| T1 | 2020-11-25 | 10 | 2020-12-04 | texture or Matt UV |  | T1 | 2020-11-28 | 12 | 2020-12-09 | texture or Matt UV |  | T1 | 2020-11-28 | 12 | 2020-12-09 | texture or Matt UV
| Production | 2020-12-22 | 10 | 2020-12-31 |  |  | Production | 2020-12-27 | 10 | 2021-01-05 |  |  | Production | 2020-12-27 | 12 | 2021-01-07
Materials | Sample order | 2020-10-16 | 14 | 2020-10-29 | for DVT/MVT | Materials | Sample order | 2020-10-16 | 14 | 2020-10-29 | for DVT/MVT | Materials | Sample order | 2020-10-16 | 14 | 2020-10-29 | for DVT/MVT
| MP 1st order | 2020-10-12 | 56 | 2020-12-06 | LL materials |  | MP 1st order | 2020-10-12 | 56 | 2020-12-06 | LL materials |  | MP 1st order | 2020-10-12 | 42 | 2020-11-22 | LL materials
| MP 2nd order | 2020-11-24 | 30 | 2020-12-23 |  |  | MP 2nd order | 2020-11-27 | 30 | 2020-12-26 |  |  | MP 2nd order | 2020-11-27 | 30 | 2020-12-26
DVT | Sample | 2020-11-13 | 4 | 2020-11-16 | 10pcs | DVT | Sample | 2020-11-16 | 4 | 2020-11-19 | 10pcs | DVT | Sample | 2020-11-16 | 4 | 2020-11-19 | 10pcs
| Magconn confirm | 2020-11-23 | 2 | 2020-11-24 |  |  | Magconn confirm | 2020-11-26 | 2 | 2020-11-27 |  |  | Magconn confirm | 2020-11-26 | 2 | 2020-11-27
MVT | Sample | 2020-12-05 | 4 | 2020-12-08 | 30pcs | MVT | Sample | 2020-12-10 | 4 | 2020-12-13 | 30pcs | MVT | Sample | 2020-12-10 | 4 | 2020-12-13 | 30pcs
| Customer confirm | 2020-12-15 | 7 | 2020-12-21 |  |  | Customer confirm | 2020-12-20 | 7 | 2020-12-26 |  |  | Customer confirm | 2020-12-20 | 7 | 2020-12-26
MP | Pilot-run | 2021-01-11 | 2 | 2021-01-12 | 100pcs | MP | Pilot-run | 2012-01-13 | 2 | 2012-01-14 | 50pcs | MP | Pilot-run | 2021-01-15 | 2 | 2021-01-16 | 50pcs
| MP | 2021-01-18 | 6 | 2021-01-23 | 2950pcs |  | MP | 2021-01-25 | 3 | 2021-01-27 | 1000pcs |  | MP | 2021-01-28 | 3 | 2021-01-30 | 1000pcs
| Shipping | 2021-02-03 | 10 | 2021-02-12 | by Ocean |  | Shipping | 2021-02-03 | 10 | 2021-02-12 | by Ocean |  | Shipping | 2021-02-03 | 10 | 2021-02-12 | by Ocean
Formulas:
End = [Start]+[Days]-1
Start = [End, row above]+1
Start = [End, row above]